## 프로젝트 플래너
Project Plan
[5 empty] | 기간 강조 표시: | 5 |  |  | planned period | [5 empty] | actual starting date |  |  |  |  | completion rate
[6 empty] | Period | [7 empty] | actual(overdue) | [5 empty] | % completion(overdue)
Activity | Planned Starting Week | Planned Period | Actual Starting Week | Actual Period | Completion Rate | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
First Meeting with Mentor | 1 | 1 | 1 | 1 | 100%
Writing Paper | 1 | 2 | 1 | 2 | 100%
Plan Presentation | 2 | 2 | 2 | 2 | 100%
Design Demo game | 3 | 3 | 3 | 3 | 100%
Design Contraction | 3 | 3 | 3 | 3 | 70%
Implementing demo games | 6 | 7 |  | 6 | 0%
Implementing System | 6 | 2 |  | 8 | 0%
Implementing Server | 6 | 2 |  | 6 | 0%
Implementing Private Blockchain | 6 | 7 |  | 3 | 0%
Implementing DB | 6 | 4 |  | 6 | 0%
Extracting Log Data | 6 | 5 |  | 7 | 0%
Distributing Log Data with Block Chain | 9 | 4 |  | 8 | 0%
Testing Demo game | 10 | 3 |  | 3 | 0%
Testing Whole System | 13 | 3 |  | 7 | 0%